## Datasheet
Datasheet
INSTRUCTIONS:
The Datasheet Section comprises Tables A, B and C, below. No additional text is required.
A. Basic Information
Country: | Regional
Project Name: | CaribData: Caribbean Data-Driven Resilience
Project Number | RG-T4186
Contract Number | ATN/OC-19725-RG
Funding Agency: | Inter-American Development Bank
Instrument: | Technical Cooperation
Implementing Agency: | University of the West Indies, Cave Hill Campus
B. Project Dates
Process | Original Date | Revised Date
IDB Approval | 2022-12-01
Contract Effectiveness | 2023-03-23
Disbursement Eligibility | 2023-07-28
Disbursement Deadline | 2026-03-23
Final Evaluation | 2026-09-23
C. Project Financials (US$)
| Total | IDB | Counterpart Resources
a. Total Budget at Approval | 685000 | 520000 | 165000
b. Revised Budget | 0
Current Semester - July 1 to December 2023
c. Planned Expenditures from July 1 to December 31, 2023 | 64410 | 41160 | 23250
d. Actual Expenditures from July 1 to December 31, 2023 | 35656 | 11156 | 24500
e. Planned IDB disbursements from July 1 to December 31, 2023 | 41160 | 41160 | 0
f. Actual IDB disbursements from July 1 to December 31, 2023 | 41160 | 41160 | 0
Next Semester - January 1 to June 30, 2024
g. Planned Expenditures from January 1 to June 30, 2024 | 145230 | 100730 | 44500
h. Planned IDB disbursements from January 1 to June 30, 2024 | 70726 | 70726 | 0

## Project Implementation Status
Project Implementation Status
Component | Consultancy | Comments
1 | Data Infrastructure and Roadmap for Data Resiliency
| Consulting firm to implement Data Visualization and Data Sharing Infrastructure Tools | Call for EOI uploaded
| Front-end support individual consultant | Contract signed 1st November
2 | Data Science Training and Knowledge Generation
| Consulting firm to provide data analytics training | Call for EOI uploaded
| Editing services | Authors identified - papers in progress
| Regional Data sharing conference | -
3 | Data Guidelines and Policies
| Individual Consultant to collate data and develop guidelines | Contract signed 1st November
4 | Project Coordination, Communication, and Evaluation
| Project assistant Individual Consultant | In process of collating CVs
Final Evaluation Individual Consultant
| Public Awareness Campaign and Marketing Activities | -
| Audit | -

## Commitments
Financial Status
Status of Commitments charged to IDB Financing (US$)
Procurement Activity | PRISM No. | Consultant | Contract Signature Date | Contract Start Date | Contract End Date | Contract Amount (USD) | Payments | Available Balance
Data Audit Consultant |  | Dr. Selvi Jeyaseelan | 2023-11-02 | 2023-10-01 | 2024-09-30 | 68000 | 9232 | 58768
Front End Support Consultant |  | Jacqueline Campbell | 2023-11-02 | 2023-10-01 | 2024-09-30 | 23088 | 1924 | 21164
Editing Services |  | Pan American Health Organization | 2023-10-19 | 2022-12-16 | 2025-01-15 | 15000 | 0 | 15000
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[5 empty] | Totals | 106088 | 11156 | 94932

## Expenditure Summary
Project Expenditure Summary
WBS | Components and Sub-components per Letter of Agreement | Cumulative amount as at the End of the Previous Reporting Period |  | Expenditure During the Reporting Period |  | Cumulative amount as at the End of the Current Reporting Period
|  | IDB | Counterpart | IDB | Counterpart | IDB | Counterpart
1 | Data Infrastructure and Roadmap for Data Resiliency | 0 | 0 | 1924 | 2000 | 1924 | 2000
2 | Data Science Training and Knowledge Generation | 0 | 0 |  | 15000 | 0 | 15000
3 | Data Guidelines and Policies | 0 | 0 | 9232 | 5000 | 9232 | 5000
4 | Project Coordination, Communication, and Evaluation | 0 | 7000 | 0 | 2500 | 0 | 9500
4.1 | Consultants to support project coordination and communication |  | 7000 | 0 | 2500 | 0 | 9500
4.2 | Public Awareness Campaign and Marketing Activities |  |  | 0 | 0 | 0 | 0
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation |  |  |  |  | 0 | 0
| Total | 0 | 7000 | 11156 | 24500 | 11156 | 31500

## Expenditure by Activity
Expenditures by Activity
| Component | Budget |  |  | Actual Expenditure |  |  | Actual to Budget %
|  | TOTAL | IDB | Counterpart | TOTAL | IDB | Counterpart | TOTAL | IDB | Counterpart
1 | Data Infrastructure and Roadmap for Data Resiliency | 180000 | 170000 | 10000 | 3924 | 1924 | 2000 | 2.18% | 1.132% | 20%
2 | Data Science Training and Knowledge Generation | 250000 | 140000 | 110000 | 15000 | 0 | 15000 | 6% | 0% | 13.64%
3 | Data Guidelines and Policies | 165000 | 135000 | 30000 | 14232 | 9232 | 5000 | 8.625% | 6.839% | 16.67%
4 | Project Coordination, Communication, and Evaluation | 90000 | 75000 | 15000 | 2500 | 0 | 2500 | 2.778% | 0% | 16.67%
4.1 | Consultants to support project coordination and communication | 55000 | 40000 | 15000 | 2500 | 0 | 2500 | 4.545% | 0% | 16.67%
4.2 | Public Awareness Campaign and Marketing Activities | 5000 | 5000 | 0 | 0 | 0 | 0 | 0% | 0% | #DIV/0!
4.3 | Audit | 10000 | 10000 | 0 | 0 | 0 | 0 | 0% | 0% | #DIV/0!
4.4 | Final Evaluation | 20000 | 20000 | 0 | 0 | 0 | 0 | 0% | 0% | #DIV/0!
| Programme Total | 685000 | 520000 | 165000 | 35656 | 11156 | 24500 | 5.205% | 2.145% | 14.85%

## Contractual Clause
Contractual Obligations
Contractual Clause | Description | Expiration Date | Revised Expiration Date | Approval Date | Status
13.i- S1 | Semi-Annual Progress Report | 2024-03-01
13.i- S2 | Semi-Annual Progress Report | 2024-09-01
13.i- S3 | Semi-Annual Progress Report | 2025-03-01
13.i- S4 | Semi-Annual Progress Report | 2025-09-01
14.a.i | Final Audited Financial Statements | 2025-12-23
13.i- S5 | Semi-Annual Progress Report | 2026-03-01
Final Disbursement | Final Disbursement Clause. | 2026-03-23
13.i- S6 | Semi-Annual Progress Report | 2026-09-01
13.ii | Final Report | 2026-09-23

## Outcome Indicators
Contractual Obligations
INSTRUCTIONS: Indicate the overall and specific objectives of the programme from the programme Results Matrix
Programme Objective | Overall objective
To improve the Caribbean's regional infrastructure for data sharing and data resilience.
Indicator Description | Unit of Measure | Baseline Amount | Baseline Year | Means of Verification |  | 2023 | 2024 | 2025 | EOP
National Statistic Offices in the Caribbean utilizing platform for sharing regional data | # | 0 | 2023 |  | P | 0 | 0 | 4 | 4
[5 empty] | P(a) | 0 | 0 | 4 | 4
[5 empty] | A | 0 | 0 | 0 | 4
Data science tools applied by the four NSO beneficiaries | % | 0 | 2022 |  | P | 0 | 0 | 100 | 100
[5 empty] | P(a) | 0 | 0 | 100 | 100
[5 empty] | A | 0 | 0 | 0 | 0

## Output Indicators.Physical
Output Indicators - Physical
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 1 | 0 | 0 | 1
|  |  |  | Planned (a) | 1 | 1 | 0 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 0 | 1 |  | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual |  |  |  | 0
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 1 | 0 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 0 | 1 | 2 | 3
|  |  |  | Actual | 0 | 0 | 0 | 0
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 0 | 2 | 2 | 4
|  |  |  | Planned (a) | 0 | 2 | 2 | 4
|  |  |  | Actual | 0 | 0 | 0 | 0
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 1 | 1 | 2
|  |  |  | Planned (a) | 0 | 1 | 1 | 2
|  |  |  | Actual | 0 | 0 | 0 | 0
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 1 | 1 | 1 | 3
|  |  |  | Actual | 1 |  |  | 1
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Output Indicators.Financial
Output Indicators - Financial
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 40000 | 0 | 0 | 40000 | 170000
|  |  |  | Planned (a) | 40000 | 38076 | 0 | 40000
|  |  |  | Actual | 1924 | 0 | 0 | 1924
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 0 | 60000 | 0 | 60000
|  |  |  | Planned (a) | 0 | 30000 | 30000 | 60000
|  |  |  | Actual | 0 | 0 | 0 | 0
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 55000 | 0 | 55000
|  |  |  | Planned (a) | 0 | 0 | 55000 | 55000
|  |  |  | Actual |  | 0 | 0 | 0
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 15000 | 15000
|  |  |  | Planned (a) | 0 | 0 | 15000 | 15000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 20000 | 50000 | 0 | 70000 | 140000
|  |  |  | Planned (a) | 20000 | 50000 | 20000 | 70000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 50000 | 0 | 50000
|  |  |  | Planned (a) | 0 | 0 | 50000 | 50000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 15000 | 5000 | 20000
|  |  |  | Actual | 0 | 0 | 0 | 0
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 30000 | 30000 | 35000 | 95000
|  |  |  | Planned (a) | 30000 | 40000 | 45768 | 95000
|  |  |  | Actual | 9232 | 0 | 0 | 9232
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 15000 | 20000 | 5000 | 40000
|  |  |  | Planned (a) | 15000 | 20000 | 20000 | 40000
|  |  |  | Actual | 0 | 0 | 0 | 0
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 2500 | 2500 | 5000
|  |  |  | Planned (a) | 0 | 2500 | 2500 | 5000
|  |  |  | Actual | 0 | 0 | 0 | 0
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 10000 | 15000 | 15000 | 40000
|  |  |  | Planned (a) | 10000 | 15000 | 25000 | 40000
|  |  |  | Actual | 0 | 0 | 0 | 0
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 0 | 20000 | 20000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Audit |  |  | Original | 0 | 0 | 10000 | 10000
|  |  |  | Planned (a) | 0 | 0 | 10000 | 10000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Total Cost |  |  | Original | 115000 | 282500 | 122500 | 520000
|  |  |  | Planned (a) | 115000 | 210576 | 298268 | 520000
|  |  |  | Actual | 11156 | 0 | 0 | 11156
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Risk Matrix
Risk Matrix
Item | Description of Risk | Risk Level | Type of Risk | Risk Impact | Mitigation Activity | Start date | End date | Responsibility | Indicator of completion of Activity
1 | UWI may find making payments in USD difficult | High | Financial | Firms and PAHO need to be paid in USD | Discuss with bursary & IDB. The meeting took place and PAHO have now been paid. | 2023-12-10 | N/A | IH | Payment of PAHO editorial fees
2 | Suitable candidate for project assistant may be hard to find | Med | Human resources | Delayed start of project assistant | Discuss possibility for split role - split role not possible | 2023-12-01 |  | SJ | Recruitment of project assistant
3 | Limited candidate firms for data story telling | Med |  | Delayed start of component 2 | Extend call for EOIs | 2023-12-01 |  | SJ | Signed contract with firm
4 | Limited candidate firms for infrastructure development | Med |  | Delayed start of component 1 | Extend call for EOIs | 2023-12-01 |  | SJ | Signed contract with firm

## Issues Log
Issues Log
Issue ref # | Date of Issue | Issue Description & Project Impact | Priority | Category | Action required | Date resolved | Comments

## Change Log
Change Log
Change ref # | Change Type | Change Description | Requested by | Date Submitted | Date Approved by IDB | Date Approved by CTO | Comments

## Lessons Learned
Lessons Learnt
Ref # | Category | Period of Observation | Lesson Learned (Problem/Success) | Impact | Recommendation | Timing if Applicable (Recommendation)

## Disbursement Projections
Disbursement Projections
| Component | Projected IDB Disbursement for next 6 months through to June 30, 2024 | [5 empty] | Total
|  | Jan | Feb | Mar | Apr | May | Jun
1 | Data Infrastructure and Roadmap for Data Resiliency | 1924 | 1924 | 1924 | 1924 | 1924 | 1924 | 11544
2 | Data Science Training and Knowledge Generation | 0 | 0 | 0 | 0 | 15000 | 0 | 15000
3 | Data Guidelines and Policies | 2308 | 8972 | 4750 | 7500 | 4500 | 9333 | 37363
4 | Project Coordination, Communication, and Evaluation | 0 | 0 | 0 | 2273 | 2273 | 2273 | 6819
4.1 | Consultants to support project coordination and communication | 0 | 0 | 0 | 2273 | 2273 | 2273 | 6819
4.2 | Public Awareness Campaign and Marketing Activities | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Programme Total* | 4232 | 10896 | 6674 | 11697 | 23697 | 13530 | 70726
Breakdown According to Disbursement Type:
A. Non-Cash - Justification of Advance
B. Cash - Advance of Funds |  | 4232 | 10896 | 6674 | 11697 | 23697 | 13530 | 70726
C. Cash - Direct Payment to Supplier |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Cash - Reimbursement of Payments Made |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Disb Total (B + C + D) |  | 4232 | 10896 | 6674 | 11697 | 23697 | 13530 | 70726
*Programme totals for each month should also be reflected in the Breakdown According to Disbursement Type schedule