## Project Implementation Status
Project Implementation Status
Component | Consultancy | Comments
1 | Data Infrastructure and Roadmap for Data Resiliency
| Consulting firm to implement Data Visualization and Data Sharing Infrastructure Tools | Due to changes in products available this activitiy is being re-structured
| Front-end support individual consultant | Contract signed 1/11/23 - Data collection infrastructure being maintained and updated. Review of data sharing platform is in progress.
2 | Data Science Training and Knowledge Generation
| Consulting firm to provide data analytics training | Firm contracted June 2024
| Editing services | Authors identified - papers under peer review
| Regional Data sharing conference | -
3 | Data Guidelines and Policies
| Individual Consultant to collate data and develop guidelines | Legislative review protocol established and review being conducted
4 | Project Coordination, Communication, and Evaluation
| Project assistant Individual Consultant | Project assistant hired. Started June 1, 2024
Final Evaluation Individual Consultant
| Public Awareness Campaign and Marketing Activities | -
| Audit | -

## Commitments
Financial Status
Status of Commitments charged to IDB Financing (US$)
Procurement Activity | PRISM No. | Consultant | Contract Signature Date | Contract Start Date | Contract End Date | Contract Amount (USD) | Payments | Available Balance
Data Audit Consultant | BAA1464 | Dr. Selvi Jeyaseelan | 2023-11-02 | 2023-10-01 | 2024-09-30 | 68000 | 16156 | 51844
Front End Support Consultant | BAA1465 | Jacqueline Campbell | 2023-11-02 | 2023-10-01 | 2024-09-30 | 23088 | 7696 | 15392
Editing Services | BAB0080 | Pan American Health Organization | 2023-10-19 | 2022-12-16 | 2025-01-15 | 15000 | 15000 | 0
Project assistant | BAA1476 | Ro-Ann Smith | 2024-05-22 | 2024-06-01 | 2024-11-30 | 11250 | 0 | 11250
Data stories training | BAA1479 | Angry Health | 2024-06-12 | 2024-06-15 | 2025-11-30 | 150000 | 0 | 150000
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[5 empty] | Totals | 267338 | 38852 | 228486

## Expenditure Summary
Project Expenditure Summary
WBS | Components and Sub-components per Letter of Agreement | Cumulative amount as at Dec 31, 2023 |  | Expenditure During Jan to June 2024 |  | Cumulative amount as at June 30, 2024
|  | IDB | Counterpart | IDB | Counterpart | IDB | Counterpart
1 | Data Infrastructure and Roadmap for Data Resiliency | 1924 | 2000 | 5772 | 5000 | 7696 | 7000
2 | Data Science Training and Knowledge Generation | 0 | 0 | 15000 | 27500 | 15000 | 27500
3 | Data Guidelines and Policies | 9232 | 5000 | 6924 | 10000 | 16156 | 15000
4 | Project Coordination, Communication, and Evaluation | 0 | 2500 | 0 | 2000 | 0 | 4500
4.1 | Consultants to support project coordination and communication |  | 2500 | 0 | 2000 | 0 | 4500
4.2 | Public Awareness Campaign and Marketing Activities |  |  | 0 | 0 | 0 | 0
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation |  |  |  |  | 0 | 0
| Total | 11156 | 9500 | 27696 | 44500 | 38852 | 54000

## Contractual Clause
Contractual Obligations
Contractual Clause | Description | Expiration Date | Revised Expiration Date | Approval Date | Status
13.i- S1 | Semi-Annual Progress Report | 2024-03-01 |  | 2024-02-29 | Fulfilled
13.i- S2 | Semi-Annual Progress Report | 2024-09-01
13.i- S3 | Semi-Annual Progress Report | 2025-03-01
13.i- S4 | Semi-Annual Progress Report | 2025-09-01
14.a.i | Final Audited Financial Statements | 2025-12-23
13.i- S5 | Semi-Annual Progress Report | 2026-03-01
Final Disbursement | Final Disbursement Clause. | 2026-03-23
13.i- S6 | Semi-Annual Progress Report | 2026-09-01
13.ii | Final Report | 2026-09-23

## Outcome Indicators
Contractual Obligations
INSTRUCTIONS: Indicate the overall and specific objectives of the programme from the programme Results Matrix
Programme Objective | Overall objective
To improve the Caribbean's regional infrastructure for data sharing and data resilience.
Indicator Description | Unit of Measure | Baseline Amount | Baseline Year | Means of Verification |  | 2023 | 2024 | 2025 | EOP
National Statistic Offices in the Caribbean utilizing platform for sharing regional data | # | 0 | 2023 |  | P | 0 | 0 | 4 | 4
[5 empty] | P(a) | 0 | 0 | 4 | 4
[5 empty] | A | 0 | 0 | 0 | 4
Data science tools applied by the four NSO beneficiaries | % | 0 | 2022 |  | P | 0 | 0 | 100 | 100
[5 empty] | P(a) | 0 | 0 | 100 | 100
[5 empty] | A | 0 | 0 | 0 | 0

## Output Indicators.Financial
Output Indicators - Financial
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 40000 | 0 | 0 | 40000
|  |  |  | Planned (a) | 40000 | 32304 | 0 | 40000
|  |  |  | Actual | 1924 | 5772 | 0 | 7696
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 0 | 60000 | 0 | 60000
|  |  |  | Planned (a) | 0 | 30000 | 30000 | 60000
|  |  |  | Actual | 0 | 0 | 0 | 0
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 55000 | 0 | 55000
|  |  |  | Planned (a) | 0 | 0 | 55000 | 55000
|  |  |  | Actual |  | 0 | 0 | 0
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 15000 | 15000
|  |  |  | Planned (a) | 0 | 0 | 15000 | 15000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 20000 | 50000 | 0 | 70000
|  |  |  | Planned (a) | 20000 | 50000 | 20000 | 70000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 50000 | 0 | 50000
|  |  |  | Planned (a) | 0 | 0 | 50000 | 50000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 15000 | 5000 | 20000
|  |  |  | Actual | 0 | 15000 | 0 | 15000
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 30000 | 30000 | 35000 | 95000
|  |  |  | Planned (a) | 30000 | 33076 | 45768 | 95000
|  |  |  | Actual | 9232 | 6924 | 0 | 16156
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 15000 | 20000 | 5000 | 40000
|  |  |  | Planned (a) | 15000 | 20000 | 20000 | 40000
|  |  |  | Actual | 0 | 0 | 0 | 0
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 2500 | 2500 | 5000
|  |  |  | Planned (a) | 0 | 2500 | 2500 | 5000
|  |  |  | Actual | 0 | 0 | 0 | 0
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 10000 | 15000 | 15000 | 40000
|  |  |  | Planned (a) | 10000 | 15000 | 25000 | 40000
|  |  |  | Actual | 0 | 0 |  | 0
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 0 | 20000 | 20000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Audit |  | Audit | Original | 0 | 0 | 10000 | 10000
|  |  |  | Planned (a) | 0 | 0 | 10000 | 10000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Total Cost |  |  | Original | 115000 | 282500 | 122500 | 520000
|  |  |  | Planned (a) | 115000 | 182880 | 298268 | 520000
|  |  |  | Actual | 11156 | 27696 | 0 | 38852
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Output Indicators.Physical
Output Indicators - Physical
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 1 | 0 | 0 | 1
|  |  |  | Planned (a) | 1 | 1 | 0 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 0 | 1 |  | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual |  |  |  | 0
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 1 | 0 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 0 | 1 | 2 | 3
|  |  |  | Actual | 0 | 0 | 0 | 0
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 0 | 2 | 2 | 4
|  |  |  | Planned (a) | 0 | 2 | 2 | 4
|  |  |  | Actual | 0 | 0 | 0 | 0
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 1 | 1 | 2
|  |  |  | Planned (a) | 0 | 1 | 1 | 2
|  |  |  | Actual | 0 | 0 | 0 | 0
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 1 | 1 | 1 | 3
|  |  |  | Actual | 1 | 0 | 0 | 1
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Risk Matrix
Risk Matrix
Item | Description of Risk | Risk Level | Type of Risk | Risk Impact | Mitigation Activity | Start date | End date | Responsibility | Indicator of completion of Activity
1 | UWI may find making payments in USD difficult | High | Financial | Firms and PAHO need to be paid in USD | Discuss with bursary & IDB. The meeting took place and PAHO have now been paid. | 2023-12-10 | N/A | IH | Payment of PAHO editorial fees
2 | Suitable candidate for project assistant may be hard to find | Med | Human resources | Delayed start of project assistant | Discuss possibility for split role - split role not possible | 2023-12-01 | 2024-06-01 | SJ | Recruitment of project assistant
3 | Limited candidate firms for data story telling | Med |  | Delayed start of component 2 | Extend call for EOIs | 2023-12-01 | 2024-06-01 | SJ | Signed contract with firm
4 | Limited candidate firms for infrastructure development | Med |  | Delayed start of component 1 | Revamping Component 1 procurement plan | 2023-12-01 |  | SJ | Signed contract with consultants
5 | Misalignment of planned activities and NSO needs |  |  | Work may not be reflected in indicator matrices | Additional needs can be addressed by project team - but this isn't reflected in the indicators tabs |  |  | SJ

## Issues Log
Issues Log
Issue ref # | Date of Issue | Issue Description & Project Impact | Priority | Category | Action required | Date resolved | Comments
| Continuous | Late payment of consultants | High |  | Developed process (to be tested) for submission of invoices to ensure with Bursary by 6th of the month |  | Process being tested - end of October will know if process works

## Change Log
Change Log
Change ref # | Change Type | Change Description | Requested by | Date Submitted | Date Approved by IDB | Date Approved by CTO | Comments
|  | Budget update | UWI | 2024-08-06 | 2024-09-10 |  |  | SAVE FOR JULY
|  | Change of outputs for Component 1 | UWI | 2024-08-06 | 2024-09-10

## Lessons Learned
Lessons Learnt
Ref # | Category | Period of Observation | Lesson Learned (Problem/Success) | Impact | Recommendation | Timing if Applicable (Recommendation)
| Consultant invoice processing | 01/24 - 09/24 | Unclear UWI process for invoice processing | Delayed payment of independent consultants | Establish accountable & transparent process & timelines for submission & payment of invoices.
| Scope of training broader than planned | 03/24 - 09/24 | 4 NSOs meant extended scope of training includes more than just data stories training in Component2 | UWI team developing training packages as well | Ensure that reporting recognises that meeting beneficiaries needs may require change in outputs

## Disbursement Projections
Disbursement Projections
| Component | Projected IDB Disbursement for next 6 months through to December 31, 2024 | [5 empty] | Total
|  | Jul | Aug | Sep | Oct | Nov | Dec
1 | Data Infrastructure and Roadmap for Data Resiliency | 1924 | 1924 | 1924 | 6924 | 13924 | 31924 | 58544
2 | Data Science Training and Knowledge Generation | 0 | 22500 | 0 | 0 | 30000 | 0 | 52500
3 | Data Guidelines and Policies | 4151 |  |  | 10300 | 5000 | 0 | 19451
4 | Project Coordination, Communication, and Evaluation | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 11250
4.1 | Consultants to support project coordination and communication | 1875 | 1875 | 1875 | 1875 | 1875 | 1875 | 11250
4.2 | Public Awareness Campaign and Marketing Activities | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Programme Total* | 7950 | 26299 | 3799 | 19099 | 50799 | 33799 | 141745
Breakdown According to Disbursement Type:
A. Non-Cash - Justification of Advance
B. Cash - Advance of Funds |  | 7950 | 26299 | 3799 | 19099 | 50799 | 33799 | 141745
C. Cash - Direct Payment to Supplier |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Cash - Reimbursement of Payments Made |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Disb Total (B + C + D) |  | 7950 | 26299 | 3799 | 19099 | 50799 | 33799 | 141745
*Programme totals for each month should also be reflected in the Breakdown According to Disbursement Type schedule