## Project Implementation Status
Project Implementation Status
Component | Consultancy | Comments
1 | Data Infrastructure and Roadmap for Data Resiliency
| Consulting firm to implement Data Visualization and Data Sharing Infrastructure Tools | Due to changes in products available this activitiy is being re-structured. The procurement plan has been updated to reflect these changes. A consultant has been engaged and associated documentation sent to IDB
| Front-end support individual consultant | Contract originally signed 1/11/23. Contract renewed 9/24 - Data collection infrastructure being maintained and updated. Data sharing platform has been identified.
2 | Data Science Training and Knowledge Generation
| Consulting firm to provide data story training | Firm contracted June 2024. Interviews conducted with NSO and training course outline has been developed and webinar delivered.
| Editing services | Special edition published in December 2024
| Regional Data sharing conference | -
3 | Data Guidelines and Policies
| Individual Consultant to collate data and develop guidelines | Legislative review protocol established and 2 gap analyses completed. Two guidelines created
4 | Project Coordination, Communication, and Evaluation
| Project assistant Individual Consultant | Project assistant hired. Started June 1, 2024 and contract renewed to December 2025
Final Evaluation Individual Consultant
| Public Awareness Campaign and Marketing Activities | CaribData team members took part in Belize Statistics Day
| Audit | -

## Commitments
Financial Status
Status of Commitments charged to IDB Financing (US$)
Procurement Activity | PRISM No. | Consultant | Contract Signature Date | Contract Start Date | Contract End Date | Contract Amount (USD) | Payments | Available Balance
Data Audit Consultant | BAA1464 | Dr. Selvi Jeyaseelan | 2023-11-02 | 2023-10-01 | 2025-09-30 | 120000 | 56490 | 63510
Front End Support Consultant | BAA1465 | Jacqueline Campbell | 2023-11-02 | 2023-10-01 | 2025-09-30 | 50000 | 17316 | 32684
Editing Services | BAB0080 | Pan American Health Organization | 2023-10-19 | 2022-12-16 | 2025-01-15 | 15000 | 15000 | 0
Project assistant | BAA1476 | Ro-Ann Smith | 2024-05-22 | 2024-06-01 | 2025-11-30 | 33750 | 9375 | 24375
Data stories training | BAA1479 | Angry Health | 2024-06-12 | 2024-06-15 | 2025-11-30 | 150000 | 15000 | 135000
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[5 empty] | Totals | 368750 | 113181 | 255569

## Expenditure Summary
Project Expenditure Summary
WBS | Components and Sub-components per Letter of Agreement | Cumulative amount as at June 30, 2024 |  | Expenditure During Jul to Dec 2024 |  | Cumulative amount as at December 31, 2024
|  | IDB | Counterpart | IDB | Counterpart | IDB | Counterpart
1 | Data Infrastructure and Roadmap for Data Resiliency | 7696 | 7000 | 9620 | 5000 | 17316 | 12000
2 | Data Science Training and Knowledge Generation | 15000 | 27500 | 15000 | 27500 | 30000 | 55000
3 | Data Guidelines and Policies | 16156 | 15000 | 40334 | 10000 | 56490 | 25000
4 | Project Coordination, Communication, and Evaluation | 0 | 4500 | 9375 | 2000 | 9375 | 6500
4.1 | Consultants to support project coordination and communication | 0 | 4500 | 9375 | 2000 | 9375 | 6500
4.2 | Public Awareness Campaign and Marketing Activities |  |  | 0 | 0 | 0 | 0
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation |  |  |  |  | 0 | 0
| Total | 38852 | 54000 | 74329 | 44500 | 113181 | 98500

## Contractual Clause
Contractual Obligations
Contractual Clause | Description | Expiration Date | Revised Expiration Date | Approval Date | Status
13.i- S1 | Semi-Annual Progress Report | 2024-03-01 |  | 2024-02-29 | Fulfilled
13.i- S2 | Semi-Annual Progress Report | 2024-09-01
13.i- S3 | Semi-Annual Progress Report | 2025-03-01
13.i- S4 | Semi-Annual Progress Report | 2025-09-01
14.a.i | Final Audited Financial Statements | 2025-12-23
13.i- S5 | Semi-Annual Progress Report | 2026-03-01
Final Disbursement | Final Disbursement Clause. | 2026-03-23
13.i- S6 | Semi-Annual Progress Report | 2026-09-01
13.ii | Final Report | 2026-09-23

## Outcome Indicators
Contractual Obligations
INSTRUCTIONS: Indicate the overall and specific objectives of the programme from the programme Results Matrix
Programme Objective | Overall objective
To improve the Caribbean's regional infrastructure for data sharing and data resilience.
Indicator Description | Unit of Measure | Baseline Amount | Baseline Year | Means of Verification |  | 2023 | 2024 | 2025 | EOP
National Statistic Offices in the Caribbean utilizing platform for sharing regional data | # | 0 | 2023 |  | P | 0 | 0 | 4 | 4
[5 empty] | P(a) | 0 | 0 | 4 | 4
[5 empty] | A | 0 | 0 | 0 | 4
Data science tools applied by the four NSO beneficiaries | % | 0 | 2022 |  | P | 0 | 0 | 100 | 100
[5 empty] | P(a) | 0 | 0 | 100 | 100
[5 empty] | A | 0 | 0 | 0 | 0

## Output Indicators.Financial
Output Indicators - Financial
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 40000 | 0 | 0 | 40000
|  |  |  | Planned (a) | 0 | 0 | 24000 | 25924
|  |  |  | Actual | 1924 | 0 | 0 | 1924
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 12000 | 19000 | 19000 | 50000
|  |  |  | Planned (a) | 0 | 25000 | 30000 | 30000
|  |  |  | Actual | 0 | 0 | 0 | 0
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 55000 | 0 | 55000
|  |  |  | Planned (a) | 0 | 0 | 32684 | 48076
|  |  |  | Actual | 0 | 15392 | 0 | 15392
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 15000 | 15000
|  |  |  | Planned (a) | 0 | 0 | 24000 | 24000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 20000 | 50000 | 0 | 70000
|  |  |  | Planned (a) | 20000 | 50000 | 110000 | 125000
|  |  |  | Actual | 0 | 15000 | 0 | 15000
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 60000 | 0 | 60000
|  |  |  | Planned (a) | 0 | 0 | 50000 | 50000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 15000 | 0 | 15000
|  |  |  | Actual | 0 | 15000 | 0 | 15000
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 30000 | 30000 | 15000 | 75000
|  |  |  | Planned (a) | 768 | 40000 | 30434 | 80000
|  |  |  | Actual | 9232 | 40334 | 0 | 49566
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 10000 | 20000 | 15000 | 45000
|  |  |  | Planned (a) | 10000 | 20000 | 33076 | 40000
|  |  |  | Actual | 0 | 6924 | 0 | 6924
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 2500 | 2500 | 5000
|  |  |  | Planned (a) | 0 | 0 | 5000 | 5000
|  |  |  | Actual | 0 | 0 | 0 | 0
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 10000 | 15000 | 15000 | 40000
|  |  |  | Planned (a) | 0 | 5625 | 40625 | 50000
|  |  |  | Actual | 0 | 9375 | 0 | 9375
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 0 | 20000 | 20000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Audit |  | Audit | Original | 0 | 0 | 10000 | 10000
|  |  |  | Planned (a) | 0 | 0 | 22000 | 22000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Total Cost |  |  | Original | 122000 | 251500 | 131500 | 505000
|  |  |  | Planned (a) | 30768 | 140625 | 421819 | 535000
|  |  |  | Actual | 11156 | 102025 | 0 | 113181
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Output Indicators.Physical
Output Indicators - Physical
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data sharing infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 1 | 0 | 0 | 1
|  |  |  | Planned (a) | 1 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 2
|  |  |  | Actual | 0 | 1 | 0 | 1
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | - | 0
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 0 | 1
|  |  |  | Actual | 0 | 1 | 0 | 1
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 0 | 1
|  |  |  | Actual | 0 | 1 | 0 | 1
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 0 | 0 | 2 | 3
|  |  |  | Actual | 0 | 1 | 0 | 1
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 0 | 2 | 2 | 4
|  |  |  | Planned (a) | 0 | 0 | 2 | 4
|  |  |  | Actual | 0 | 2 | 0 | 2
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 1 | 1 | 2
|  |  |  | Planned (a) | 0 | 0 | 1 | 2
|  |  |  | Actual | 0 | 1 | 0 | 1
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 1 | 0 | 1 | 3
|  |  |  | Actual | 1 | 1 | 0 | 2
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Risk Matrix
Risk Matrix
Item | Description of Risk | Risk Level | Type of Risk | Risk Impact | Mitigation Activity | Start date | End date | Responsibility | Indicator of completion of Activity
1 | UWI may find making payments in USD difficult | High | Financial | Firms and PAHO need to be paid in USD | Discuss with bursary & IDB. The meeting took place and PAHO have now been paid. | 2023-12-10 | N/A | IH | Payment of PAHO editorial fees
2 | Suitable candidate for project assistant may be hard to find | Med | Human resources | Delayed start of project assistant | Discuss possibility for split role - split role not possible | 2023-12-01 | 2024-06-01 | SJ | Recruitment of project assistant
3 | Limited candidate firms for data story telling | Med |  | Delayed start of component 2 | Extend call for EOIs | 2023-12-01 | 2024-06-01 | SJ | Signed contract with firm
4 | Limited candidate firms for infrastructure development | Med |  | Delayed start of component 1 | Revamping Component 1 procurement plan | 2023-12-01 | 2024-12-10 | SJ | Signed contract with consultants
5 | Misalignment of planned activities and NSO needs | HIgh |  | Work may not be reflected in indicator matrices | Additional needs can be addressed by project team - but this isn't reflected in the indicators tabs | 2024-06-01 |  | ALL
6 | Lack of engagement with NSO | High |  | Ability to fulfill indicators will be severely hampered | Identifying alternative sources of data for sharing and story telling | 2024-06-01 |  | ALL | Data stories produces & data shared
7 | UWI not paying invoices within 30 day | High | Financial/ Human resources | Halting of project activities by those not paid | Escalation to IDB | 2024-08-01 |  | IDB | All invoices processed within 30 days
8 | UWI not providing monthly statements in timely manner (i.e not a monthly or quarterly basis) | High | Financial | Real time tracking of budget & regularisation of disbursement is impossible | Escalation to IDB | 2024-06-01 |  | IDB | Monthly statements arriving within first 2 weeks of following month
9 | UWI statements only summary of monthly expenditure | HIgh | Financial | Real time tracking of budget is difficult | Escalation to IDB | 2024-06-01 |  | ALL | Monthly statements comprise itemised transaction list

## Issues Log
Issues Log
Issue ref # | Date of Issue | Issue Description & Project Impact | Priority | Category | Action required | Date resolved | Comments
| Continuous | Late payment of consultants | High |  | Developed process (to be tested) for submission of invoices to ensure with Bursary by 6th of the month |  | Process being tested - end of October will know if process works. This process has failed and is being hampered by issue 2.
| Continuous | UWI not providing detailed monthly statements in timely manner (i.e not a monthly or quarterly basis) | High |  | Detailed monthly statements arriving within first 2 weeks of following month - issue has been flagged but no change.
| Continuous | Lack of NSO engagement | High |  | Need to identify alternative sources of data for storytelling and sharing

## Change Log
Change Log
Change ref # | Change Type | Change Description | Requested by | Date Submitted | Date Approved by IDB | Date Approved by CTO | Comments
|  | Budget update | UWI | 2024-08-06 | 2024-09-10 |  |  | SAVE FOR JULY
|  | Change of outputs for Component 1 | UWI | 2024-08-06 | 2024-09-10
|  | Broadening of potential data sources beyond NSOs and 4 beneficiary countries | UWI | 2025-01-27

## Lessons Learned
Lessons Learnt
Ref # | Category | Period of Observation | Lesson Learned (Problem/Success) | Impact | Recommendation | Timing if Applicable (Recommendation)
| Consultant invoice processing | 01/24 - 09/24 | Unclear UWI process for invoice processing | Delayed payment of independent consultants | Establish accountable & transparent process & timelines for submission & payment of invoices.
| Scope of training broader than planned | 03/24 - 09/24 | 4 NSOs meant extended scope of training includes more than just data stories training in Component2 | UWI team developing training packages as well | Ensure that reporting recognises that meeting beneficiaries needs may require change in outputs
| C2- Data sources | 06/24-12/24 | Need broader range of data sources needed due to poor NSO engagement | Limited data sources and interest in courses | UWI team broadening data sources

## Disbursement Projections
Disbursement Projections
| Component | Projected IDB Disbursement for next 6 months through to June 30, 2025 | [5 empty] | Total
|  | Jan | Feb | Mar | Apr | May | Jun
1 | Data Infrastructure and Roadmap for Data Resiliency | 3848 | 8168 | 11288 | 9368 | 9128 | 5288 | 47088
2 | Data Science Training and Knowledge Generation | 0 | 30000 | 30000 | 15000 | 22500 | 30000 | 127500
3 | Data Guidelines and Policies | 0 | 17330 | 10000 | 7500 | 5000 | 12500 | 52330
4 | Project Coordination, Communication, and Evaluation | 3750 | 3750 | 3750 | 8750 | 3750 | 3750 | 27500
4.1 | Consultants to support project coordination and communication | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 22500
4.2 | Public Awareness Campaign and Marketing Activities | 0 | 0 | 0 | 5000 | 0 | 0 | 5000
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Programme Total* | 7598 | 59248 | 55038 | 40618 | 40378 | 51538 | 254418
Breakdown According to Disbursement Type:
A. Non-Cash - Justification of Advance
B. Cash - Advance of Funds |  | 7598 | 59248 | 55038 | 40618 | 40378 | 51538 | 254418
C. Cash - Direct Payment to Supplier |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Cash - Reimbursement of Payments Made |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Disb Total (B + C + D) |  | 7598 | 59248 | 55038 | 40618 | 40378 | 51538 | 254418
*Programme totals for each month should also be reflected in the Breakdown According to Disbursement Type schedule