## Project Implementation Status
Project Implementation Status
Component | Consultancy | Comments
1 | Data Infrastructure and Roadmap for Data Resiliency
| Consulting firm to implement Data Visualization and Data Sharing Infrastructure Tools | Due to changes in products available this activitiy is being re-structured. 12/24 The procurement plan has been updated to reflect these changes. A consultant has been engaged and associated documentation sent to IDB.
| Front-end support individual consultant | Contract originally signed 1/11/23. Contract renewed 9/24 - Data collection infrastructure established & maintained with sustainability plan in place. Data sharing and training platforms have been identified. REDCap training courses tested and delivered. Course handover scheduled for July 2025. Contract due to end Sept 2025 - have requested contract extension and virement from Component 4 underspend
2 | Data Science Training and Knowledge Generation
| Consulting firm to provide data story training | Firm contracted June 2024. Interviews conducted with NSO and training needs identified. Training course outline has been developed. One training session has already been deliverd (via UWI) 12/2024. The training course content has been beta tested with NSOs and amended in line with comments. Second feedback session planned for end of July.
| Editing services | Special edition published in December 2024
| Regional Data sharing conference | Data storython planned for September 2025. Agreed that prize money from 1.4 be allocated to Angry Health to organise prize giving and procure services for datathon hosting. Non-objection request has been submitted.
3 | Data Guidelines and Policies
| Individual Consultant to collate data and develop guidelines | 2 legislative reviews completed - one regional and one for Belize reviewing capacity for open data. Regional data legislation sent to PSC for review with comments due end of July. Belize review is currently with NSO team for comments/feedback. 2 guidelines created covering data sharing and data reuse. Remaining 2 policies/guide will be Belize specific - so topics TBC
4 | Project Coordination, Communication, and Evaluation
| Project assistant Individual Consultant | Project assistant hired. Started June 1, 2024 and contract renewed to end of Nov 2025. Assistant has been providing assistance with data stories and updating social media channels
Final Evaluation Individual Consultant
| Public Awareness Campaign and Marketing Activities | CaribData team members took part in Belize Statistics Day. Data stories webpage is up.
Three quotes were obtained and an evaluation completed. A supplier has been identified and a non-objection request to hire the supplier has been submitted.
| Audit | -

## Commitments
Financial Status
Status of Commitments charged to IDB Financing (US$)
Procurement Activity | PRISM No. | Consultant | Contract Signature Date | Contract Start Date | Contract End Date | Contract Amount (USD) | Payments | Available Balance
Front End Support Consultant | BAA1465 | Jacqueline Campbell | 2023-11-02 | 2023-10-01 | 2025-09-30 | 50000 | 36556 | 13444
Impact readiness assessment | 19/Jan - request sent | George Helliar | 2025-01-16 | 2024-12-01 | 2025-11-30 | 24000 | 4320 | 19680
Editing Services | BAB0080 | Pan American Health Organization | 2023-10-19 | 2022-12-16 | 2025-01-15 | 15000 | 15000 | 0
Data stories training | BAA1479 | Angry Health | 2024-06-12 | 2024-06-15 | 2026-01-14 | 150000 | 45000 | 105000
Data Audit Consultant | BAA1464 | Dr. Selvi Jeyaseelan | 2023-11-02 | 2023-10-01 | 2025-09-30 | 120000 | 71820 | 48180
Project assistant | BAA1476 | Ro-Ann Smith | 2024-05-22 | 2024-06-01 | 2025-11-30 | 33750 | 22500 | 11250
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[5 empty] | Totals | 392750 | 195196 | 197554

## Expenditure Summary
Project Expenditure Summary
WBS | Components and Sub-components per Letter of Agreement | Cumulative amount as at 31 December 2024 |  | Expenditure During Jan to Jun 2025 |  | Cumulative amount as at 30, June 2025
|  | IDB | Counterpart | IDB | Counterpart | IDB | Counterpart
1 | Data Infrastructure and Roadmap for Data Resiliency | 17316 | 12000 | 23560 | 4000 | 40876 | 16000
2 | Data Science Training and Knowledge Generation | 30000 | 55000 | 30000 | 28750 | 60000 | 83750
3 | Data Guidelines and Policies | 66820 | 25000 | 5000 | 10000 | 71820 | 35000
4 | Project Coordination, Communication, and Evaluation | 9375 | 6500 | 13125 | 6000 | 22500 | 12500
4.1 | Consultants to support project coordination and communication | 9375 | 6500 | 13125 | 6000 | 22500 | 12500
4.2 | Public Awareness Campaign and Marketing Activities |  |  | 0 | 0 | 0 | 0
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation |  |  |  |  | 0 | 0
| Total | 123511 | 98500 | 71685 | 48750 | 195196 | 147250

## Contractual Clause
Contractual Obligations
Contractual Clause | Description | Expiration Date | Revised Expiration Date | Approval Date | Status | Submitted date
13.i- S1 | Semi-Annual Progress Report | 2024-03-01 |  | 2024-02-29 | Fulfilled
13.i- S2 | Semi-Annual Progress Report | 2024-09-01 |  |  |  | 2024-07-01
13.i- S3 | Semi-Annual Progress Report | 2025-03-01 |  |  |  | 2025-01-20
13.i- S4 | Semi-Annual Progress Report | 2025-09-01
14.a.i | Final Audited Financial Statements | 2025-12-23
13.i- S5 | Semi-Annual Progress Report | 2026-03-01
Final Disbursement | Final Disbursement Clause. | 2026-03-23
13.i- S6 | Semi-Annual Progress Report | 2026-09-01
13.ii | Final Report | 2026-09-23

## Outcome Indicators
Contractual Obligations
INSTRUCTIONS: Indicate the overall and specific objectives of the programme from the programme Results Matrix
Programme Objective | Overall objective
To improve the Caribbean's regional infrastructure for data sharing and data resilience.
Indicator Description | Unit of Measure | Baseline Amount | Baseline Year | Means of Verification |  | 2023 | 2024 | 2025 | EOP
National Statistic Offices in the Caribbean utilizing platform for sharing regional data | # | 0 | 2023 |  | P | 0 | 0 | 4 | 4
[5 empty] | P(a) | 0 | 0 | 4 | 4
[5 empty] | A | 0 | 0 | 0 | 4
Data science tools applied by the four NSO beneficiaries | % | 0 | 2022 |  | P | 0 | 0 | 100 | 100
[5 empty] | P(a) | 0 | 0 | 100 | 100
[5 empty] | A | 0 | 0 | 0 | 0

## Output Indicators.Financial
Output Indicators - Financial
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 40000 | 0 | 0 | 40000
|  |  |  | Planned (a) | 0 | 0 | 24000 | 30244
|  |  |  | Actual | 1924 | 0 | 4320 | 6244
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 12000 | 19000 | 19000 | 50000
|  |  |  | Planned (a) | 0 | 25000 | 30000 | 30000
|  |  |  | Actual | 0 | 0 | 0 | 0
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 55000 | 0 | 55000
|  |  |  | Planned (a) | 0 | 0 | 28836 | 67316
|  |  |  | Actual | 0 | 19240 | 19240 | 38480
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 15000 | 15000
|  |  |  | Planned (a) | 0 | 0 | 24000 | 24000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 20000 | 50000 | 0 | 70000
|  |  |  | Planned (a) | 20000 | 50000 | 110000 | 155000
|  |  |  | Actual | 0 | 15000 | 30000 | 45000
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 60000 | 0 | 60000
|  |  |  | Planned (a) | 0 | 0 | 50000 | 50000
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 15000 | 0 | 15000
|  |  |  | Actual | 0 | 15000 | 0 | 15000
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 30000 | 30000 | 15000 | 75000
|  |  |  | Planned (a) | 768 | 40000 | 30434 | 90330
|  |  |  | Actual | 9232 | 50664 | 0 | 59896
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 10000 | 20000 | 15000 | 45000
|  |  |  | Planned (a) | 10000 | 20000 | 33076 | 45000
|  |  |  | Actual | 0 | 6924 | 5000 | 11924
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 2500 | 2500 | 5000
|  |  |  | Planned (a) | 0 | 0 | 5000 | 5000
|  |  |  | Actual | 0 | 0 | 0 | 0
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 10000 | 15000 | 25000 | 50000
|  |  |  | Planned (a) | 0 | -7500 | 40625 | 76250
|  |  |  | Actual | 0 | 22500 | 13125 | 35625
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 20000 | 20000
|  |  |  | Planned (a) | 0 | 0 | 20000 | 20000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Audit |  | Audit | Original | 0 | 0 | 10000 | 10000
|  |  |  | Planned (a) | 0 | 0 | 22000 | 22000
|  |  |  | Actual | 0 | 0 | 0 | 0
| Total Cost |  |  | Original | 122000 | 251500 | 141500 | 515000
|  |  |  | Planned (a) | 30768 | 127500 | 417971 | 630140
|  |  |  | Actual | 11156 | 129328 | 71685 | 212169
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Output Indicators.Physical
Output Indicators - Physical
Indicator # | Output Name | Output Description | Unit of Measure |  | 2023 | 2024 | 2025 | EOP
1.1 | Diagnostics and assessments completed | A systems analysis of the existing data sharing infrastructure and capabilities within The UWI and the NSO beneficiaries of the project | Diagnostics (#) | Original | 1 | 0 | 0 | 1
|  |  |  | Planned (a) | 1 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
1.2 | Tools designed/strengthened | Existing infrastructure tool strengthened | Tools (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 0 | 2
|  |  |  | Actual | 0 | 1 | 1 | 2
1.3 | Training workshops delivered | Training workshops and mentoring to guide NSOs | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 0 | 1
|  |  |  | Actual | 0 | 0 | 1 | 1
1.4 | Strategies designed | Roadmap strategy for the regional network which will recommend expansion of data themes | Strategies (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.1 | Training workshops delivered | Preparation and delivery of 2 data handling courses | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 0 | 1
|  |  |  | Actual | 0 | 1 | 0 | 1
2.2 | Workshops organized | Datathon designed and implemented | Workshops (#) | Original | 0 | 1 | 0 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
2.3 | Monographs developed | The publication of a curated series of data stories on priority issues in climate change and health | Monographs (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 0 | 1
|  |  |  | Actual | 0 | 1 | 0 | 1
3.1 | Diagnostics and assessments completed | Gap analysis of data handling, data sharing, data privacy, data security, and open data policies | Diagnostics (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 0 | 0 | 0 | 3
|  |  |  | Actual | 0 | 1 | 2 | 3
3.2 | Policy briefs completed | At least 4 draft data policies and guidelines developed | Briefs (#) | Original | 0 | 2 | 2 | 4
|  |  |  | Planned (a) | 0 | 0 | 2 | 4
|  |  |  | Actual | 0 | 2 | 0 | 2
4.1 | Awareness raising campaigns designed/implemented | Public Awareness Campaign and Marketing Activities | Campaigns (#) | Original | 0 | 1 | 1 | 2
|  |  |  | Planned (a) | 0 | 0 | 1 | 2
|  |  |  | Actual | 0 | 1 | 0 | 1
4.2 | Annual reports published | Annual reports on project progress | Reports (#) | Original | 1 | 1 | 1 | 3
|  |  |  | Planned (a) | 1 | 0 | 1 | 3
|  |  |  | Actual | 1 | 1 | 0 | 2
4.3 | Process evaluations conducted | Final project evaluation | Evaluation Final Report (#) | Original | 0 | 0 | 1 | 1
|  |  |  | Planned (a) | 0 | 0 | 1 | 1
|  |  |  | Actual | 0 | 0 | 0 | 0
*Planned (a) EOP = Planned (a) of Current and Subsequent Years + Actual EOP

## Risk Matrix
Risk Matrix
Item | Description of Risk | Risk Level | Type of Risk | Risk Impact | Mitigation Activity | Start date | End date | Responsibility | Indicator of completion of Activity
1 | UWI may find making payments in USD difficult | High | Financial | Firms and PAHO need to be paid in USD | Discuss with bursary & IDB. The meeting took place and PAHO have now been paid. | 2023-12-10 | N/A | IH | Payment of PAHO editorial fees
2 | Suitable candidate for project assistant may be hard to find | Med | Human resources | Delayed start of project assistant | Discuss possibility for split role - split role not possible | 2023-12-01 | 2024-06-01 | SJ | Recruitment of project assistant
3 | Limited candidate firms for data story telling | Med |  | Delayed start of component 2 | Extend call for EOIs | 2023-12-01 | 2024-06-01 | SJ | Signed contract with firm
4 | Limited candidate firms for infrastructure development | Med |  | Delayed start of component 1 | Revamping Component 1 procurement plan | 2023-12-01 | 2024-12-10 | SJ | Signed contract with consultants
5 | Misalignment of planned activities and NSO needs | HIgh |  | Work may not be reflected in indicator matrices | Additional needs can be addressed by project team - but this isn't reflected in the indicators tabs | 2024-06-01 | 2024-06-06 | ALL | Resolved as GUY using REDCap
6 | Lack of engagement with NSO for data stories | High |  | Ability to fulfill indicators will be severely hampered | Identifying alternative sources of data for sharing and story telling IDB providing support with obtaining NSO engagement for training | 2024-06-01 |  | ALL | Data stories produces & data shared
7 | UWI not paying consultant invoices within 30 day | High | Financial/ Human resources | Halting of project activities by those not paid | Escalation to IDB | 2024-08-01 | 2025-01-30 | IDB | All invoices processed within 30 days
8 | UWI not providing monthly statements in timely manner (i.e not a monthly or quarterly basis) | High | Financial | Real time tracking of budget & regularisation of disbursement is impossible | Escalation to IDB | 2024-06-01 | 2025-06-30 | IDB | Monthly statements arriving within first 2 weeks of following month
9 | UWI not paying consultant invoices within 30 day | Med | Financial/Outputs | AH being flexible but maybe issue with remaining firms | Monitoring | 2025-03-01 |  | UWI
10 | Data audit consultant contract end 09/25 | Low | Reporting | Could affect final report submission | Consultant to complete final report as much as possible before 30/9/25 and work with project lead prior to submission | 2024-06-30 |  | SJ & IH | Submission of final reports

## Issues Log
Issues Log
Issue ref # | Date of Issue | Issue Description & Project Impact | Priority | Category | Action required | Date resolved | Comments
| Continuous | Late payment of consultants | High |  | Developed process (to be tested) for submission of invoices to ensure with Bursary by 6th of the month | 2025-01-30
| Continuous | UWI not providing detailed monthly statements in timely manner (i.e not a monthly or quarterly basis) | High |  | Detailed monthly statements arriving within first 2 weeks of following month - issue has been flagged but no change. | 2025-05-01 | Statements for 2025 were provided in a timely manner
| Continuous | Lack of NSO engagement | High |  | Need to identify alternative sources of data for storytelling and utilise IDB team to circulate invitations to training events and datathon

## Change Log
Change Log
Change ref # | Change Type | Change Description | Requested by | Date Submitted | Date Approved by IDB | Date Approved by CTO | Comments
|  | Budget update | UWI | 2024-08-06 | 2024-09-10 |  |  | SAVE FOR JULY
|  | Change of outputs for Component 1 | UWI | 2024-08-06 | 2024-09-10
|  | Broadening of potential data sources beyond NSOs and 4 beneficiary countries | UWI | 2025-01-27

## Lessons Learned
Lessons Learnt
Ref # | Category | Period of Observation | Lesson Learned (Problem/Success) | Impact | Recommendation | Timing if Applicable (Recommendation)
| Consultant invoice processing | 01/24 - 09/24 | Unclear UWI process for invoice processing | Delayed payment of independent consultants | Establish accountable & transparent process & timelines for submission & payment of invoices.
| Scope of training broader than planned | 03/24 - 09/24 | 4 NSOs meant extended scope of training includes more than just data stories training in Component2 | UWI team developing training packages as well | Ensure that reporting recognises that meeting beneficiaries needs may require change in outputs
| C2- Data sources | 06/24-12/24 | Need broader range of data sources needed due to poor NSO engagement | Limited data sources and interest in courses | UWI team broadening data sources

## Disbursement Projections
Disbursement Projections
| Component | Projected IDB Disbursement for next 6 months through to Dec 31, 2025 | [5 empty] | Total
|  | Jul | Aug | Sep | Oct | Nov | Dec
1 | Data Infrastructure and Roadmap for Data Resiliency | 0 | 8168 | 11288 | 9368 | 9128 | 5288 | 43240
2 | Data Science Training and Knowledge Generation | 0 | 30000 | 30000 | 15000 | 22500 | 30000 | 127500
3 | Data Guidelines and Policies | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Project Coordination, Communication, and Evaluation | 5000 | 3750 | 3750 | 3750 | 3750 | 3750 | 23750
4.1 | Consultants to support project coordination and communication | 0 | 3750 | 3750 | 3750 | 3750 | 3750 | 18750
4.2 | Public Awareness Campaign and Marketing Activities | 5000 | 0 | 0 |  | 0 | 0 | 5000
4.3 | Audit | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Final Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Programme Total* | 5000 | 41918 | 45038 | 28118 | 35378 | 39038 | 194490
Breakdown According to Disbursement Type:
A. Non-Cash - Justification of Advance
B. Cash - Advance of Funds |  | 5000 | 41918 | 45038 | 28118 | 35378 | 39038 | 194490
C. Cash - Direct Payment to Supplier |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Cash - Reimbursement of Payments Made |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Disb Total (B + C + D) |  | 5000 | 41918 | 45038 | 28118 | 35378 | 39038 | 194490
*Programme totals for each month should also be reflected in the Breakdown According to Disbursement Type schedule